## Summary
Contract Valuation
Contract |  |  | Two Rivers FY17/18- Leaseholder Blocks
Client |  |  | Two Rivers Housing
Form of Contract |  |  | TPC 2005
Contract Final Date for Payment |  |  | 31st March 2018
Contract Sum |  |  | 43146.2846
Forecast Final Account |  |  | 51775.5415
See attached detailed schedules
| WORK TOTALS |  |  | Forecast Final Account
Preliminaries |  |  |  |  | 0
Measured Works |  |  |  |  | 40285.98
Overheads |  | 5% |  |  | 2014.299
Profit |  | 2% |  |  | 846.0056
Total |  | Exc VAT |  |  | 43146.2846
VAT |  | 20% |  |  | 8629.2569
Total |  |  |  |  | 51775.5415
| Address |  | Cost | Plus COO & P | Property Numbers | Cost per Property | Cost Plus VAT
19-25 | Albert Street |  | 1059.51 | 1134.7352 | 4 | 283.6838 | 340.4206
17-20 | Aylands Close |  | 812.1 | 869.7591 | 4 | 217.4398 | 260.9277
13-16 | Aylands Close |  | 861.82 | 923.0092 | 4 | 230.7523 | 276.9028
9-12 | Aylands Close |  | 1052.11 | 1126.8098 | 4 | 281.7025 | 338.0429
1-4 | Aylands Close |  | 684.81 | 733.4315 | 4 | 183.3579 | 220.0295
21-32 | Aylands Close |  | 4131.4 | 4424.7294 | 12 | 368.7275 | 442.4729
2-12 | Colchester Close |  | 1500.49 | 1607.0248 | 6 | 267.8375 | 321.405
79-93 | Glebe Road |  | 4766.36 | 5104.7716 | 8 | 638.0964 | 765.7157
58-72 | Harriosnway |  | 3233.21 | 3462.7679 | 8 | 432.846 | 519.4152
30-32 | Harriosnway |  | 1069.6 | 1145.5416 | 3 | 381.8472 | 458.2166
25-32 | Jubilee Place |  | 2475.73 | 2651.5068 | 8 | 331.4384 | 397.726
13-22 | Leaze Court |  | 4439.6 | 4754.8116 | 10 | 475.4812 | 570.5774
1-8 | Manor Court |  | 964.8 | 1033.3008 | 8 | 129.1626 | 154.9951
43-44 | Oakfields |  | 413.15 | 442.4837 | 4 | 110.6209 | 132.7451
33-34 | Oakfields |  | 1234.35 | 1321.9888 | 4 | 330.4972 | 396.5967
2-3 | Silley Close |  | 624.17 | 668.4861 | 2 | 334.243 | 401.0916
14-14d | Smithville Close |  | 756.23 | 809.9223 | 4 | 202.4806 | 242.9767
14-17 | St Mary's Square |  | 778.84 | 834.1376 | 4 | 208.5344 | 250.2413
2-5 | St Mary's Square |  | 687.65 | 736.4732 | 4 | 184.1183 | 220.9419
7-10 | Sunnymead Close |  | 846.9 | 907.0299 | 4 | 226.7575 | 272.109
1-6 | Tuthill Rise |  | 677.3 | 725.3883 | 6 | 120.898 | 145.0777
| Wyndcliffe House |  | 5091.41 | 5452.9001 | 6 | 908.8167 | 1090.58
8-14 | Wynols Close |  | 1418.35 | 1519.0529 | 4 | 379.7632 | 455.7159
1-7 | Wynols Close |  | 706.09 | 756.2224 | 4 | 189.0556 | 226.8667

## Surveyed Works
| Two Rivers FY17/18- Leaseholder Blocks | [5 empty] | 1/100 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
[7 empty] | Nr | 19-25 | 17-20 | 13-16 | 9-12 | 1-4 | 21-32 | 2-12 | 79-93 | 58-72 | 30-32 | 25-32 | 13-22 | 1-8 | 43-44 | 33-34 | 2-3 | 14a-14d | 14-17 | 2-5 | 7-10 | 1-6 |  | 8-14 | 1-7
[7 empty] | Street | Albert Street | Aylands Close | Aylands Close | Aylands Close | Aylands Close | Aylands Close | Colchester Close | Glebe Road | Harrison Way | Harrison Way | Jubilee Place | Leaze Court | Manor Court | Oakfields | Oakfields | Silleys Close | Smithville Close | St Mary's Square | St Mary's Square | Sunnymead Close | Tutshill Rise | Wyndcliffe House | Wynols Close | Wynols Close
[6 empty] | Total | 40285.98 | 1059.51 | 812.1 | 861.82 | 1052.11 | 684.81 | 4131.4 | 1500.49 | 4766.36 | 3233.21 | 1069.6 | 2475.73 | 4439.6 | 964.8 | 413.15 | 1234.35 | 624.17 | 756.23 | 778.84 | 687.65 | 846.9 | 677.3 | 5091.41 | 1418.35 | 706.09
Order | SOR Code | Work Element | Description | Quantity | Uom | Rate | Total Cost
1 | AS013 | E7 General | ASBESTOS:Removal of asebestos cement soffit from two elevations on a single dwelling. Including integral porch up to a max of 16 LM | 0 | IT | 109.19 | 0
2 | AS025 | E7 General | ASBESTOS:Encapsulate asbestos cement/AIB soffits | 0 | LM | 13.1 | 0
3 | Asbestos sealings | E8 Internal Structure & Finishes | Seal asbestos soffit board | 0 | M | 2.73 | 0
4 | BR002 | E2 External Walls | WALL:DEMOLISH EXTERNAL 1B WALL | 0 | SM | 18.52 | 0
5 | BR003 | E2 External Walls | WALL:DEMOLISH EXTERNAL 1-1/2B WALL | 0 | SM | 29.94 | 0
6 | BR004 | E2 External Walls | WALL:DEMOLISH EXTERNAL CAVITY WALL | 0 | SM | 17.53 | 0
7 | BR014 | E2 External Walls | WALL:BUILD 1B WALL IN FACINGS | 0 | SM | 112.22 | 0
8 | BR015 | E2 External Walls | WALL:NEW CAVITY WALL IN FACINGS | 0 | SM | 113.96 | 0
9 | BR020 | E2 External Walls | WALL:REBUILD 1B WALL IN COMMONS | 0 | SM | 86.73 | 0
10 | BR022 | E2 External Walls | WALL:REBUILD 1B WALL IN FACINGS | 0 | SM | 123.47 | 0
11 | BR030 | E2 External Walls | PIER:REBUILD 1B WIDE ATTACHED IN FACINGS | 0 | LM | 25.45 | 0
12 | BR038 | E2 External Walls | WALL:REPAIR LARGE PATCH IN FACINGS | 0 | IT | 90.9 | 0
13 | BR041 | E2 External Walls | WALL:RENEW INDIVIDUAL 225MM BLOCK | 0 | NO | 8.51 | 0
14 | BR044 | E2 External Walls | Fill Crack to Mortar | 0 | LM | 1.97 | 0
15 | BR056 | E4 Windows & Doors | LINTOL:RENEW PCC LINTOL NE 1.5M LONG | 0 | NO | 61.65 | 0
16 | BR057 | E4 Windows & Doors | LINTOL:RENEW PCC LINTOL OVER 1.5M LONG | 0 | NO | 92.8 | 0
17 | BR065 | E4 Windows & Doors | CILL:MAKE GOOD DAMAGED CONCRETE CILL | 0 | NO | 28.51 | 0
18 | BR075 | E2 External Walls | COPING:REBED BRICK ON EDGE COPING | 0 | LM | 15.65 | 0
19 | BR076 | E2 External Walls | COPING:LAY NEW BRICK ON EDGE COPING | 0 | LM | 17.55 | 0
20 | BR077 | E2 External Walls | COPING:REBED PCC COPING | 0 | LM | 4.56 | 0
21 | BR081 | E5 Environmental | CANOPIES: REMOVE PCC CANOPY ABOVE ANY DOORWAY | 0 | IT | 97.99 | 0
22 | BR083 | E5 Environmental | Royale with georgian décor legs | 0 | IT | 189.21 | 0
23 | BR097 | E1 Roofs | CHIMNEY:REBUILD 4 COURSE 1 FLUE | 0 | IT | 75.62 | 0
24 | BR099 | E1 Roofs | CHIMNEY:REBUILD 4 COURSE 2 FLUE | 0 | IT | 137.85 | 0
25 | BR100 | E1 Roofs | CHIMNEY:REBUILD 1 COURSE 2 FLUE | 0 | IT | 19 | 0
26 | BR101 | E1 Roofs | CHIMNEY:REBUILD 4 COURSE 4 FLUE | 0 | IT | 236.41 | 0
27 | BR105 | E1 Roofs | CHIMNEY:REBUILD 4 COURSE 8 FLUE | 0 | IT | 517.25 | 0
28 | BR106 | E1 Roofs | CHIMNEY:REBUILD 1 COURSE 8 FLUE | 0 | IT | 56 | 0
29 | BR107 | E1 Roofs | CHIMNEY:DEMOLISH STACK AND MAKE GOOD ROOF | 0 | IT | 171.99 | 0
30 | BR110 | E1 Roofs | CHIMNEY:RENEW BRICKS NE 0.50SM | 0 | NO | 51.24 | 0
31 | BR113 | E1 Roofs | CHIMNEY:RENEW POT NE 600MM HIGH | 0 | NO | 53.89 | 0
32 | BR117 | E1 Roofs | CHIMNEY:REBED POT | 0 | NO | 11.81 | 0
33 | BR119 | E1 Roofs | CHIMNEY:INSTALL AEROCOWL TO POT | 0 | NO | 61.38 | 0
34 | BR123 | E1 Roofs | CHIMNEY:REMOVE AND REFIX TV AERIAL OR DISH | 0 | NO | 9 | 0
35 | BR124 | E7 General | METER CUPBOARD:RENEW OR SUPPLY AND FIX NEW | 0 | NO | 43.78 | 0
36 | BR125 | E7 General | METER CUPBOARD:RENEW DOOR | 0 | NO | 21.49 | 0
37 | BT Cable | E7 General | Remove and refix BT cable | 0 | IT | 121.54 | 0
38 | CHIC 101101 | E2 External Walls | Demolish external 1/2 brick thick wall | 0 | M2 | 13.07 | 0
39 | CHIC 101103 | E2 External Walls | Demolish external 1 brick thick wall | 0 | M2 | 22.69 | 0
40 | CHIC 101309 | E2 External Walls | Build 1/2 brick thick wall in facing bricks | 0 | M2 | 53.57 | 0
41 | CHIC 101511 | E2 External Walls | Rebuild 100mm block wall | 0 | M2 | 23.28 | 0
42 | CHIC 101907 | E2 External Walls | Repair small patch in facing bricks | 0 | IT | 44.31 | 0
43 | CHIC 101909 | E2 External Walls | Repair large patch in facings | 0 | IT | 88.62 | 0
44 | CHIC 102103 | E2 External Walls | Rake out and repoint brickwork | 271 | M2 | 32.09 | 8696.39 | 3 | 4 | 4 | 5 | 1 | 10 | 20 | 20 | 89 | 10 | 5 | 42 | 8 | 5 | 10 |  | 5 |  |  |  | 10 | 10 | 10
45 | CHIC 102719 | E2 External Walls | Make good hole any diameter | 0 | No | 22.23 | 0
46 | CHIC 103101 | E2 External Walls | Renew single quarry tile | 0 | No | 8.36 | 0
47 | CHIC 103103 | E2 External Walls | Renew cill with 2 course quarry tiles | 0 | M | 31.65 | 0
48 | CHIC 103107 | E4 Windows & Doors | Renew PCC cill | 0 | M | 38.03 | 0
49 | CHIC 103307 | E2 External Walls | Rebed PCC Coping | 0 | M | 22.03 | 0
50 | CHIC 103311 | E2 External Walls | Lay new PPC coping | 0 | M | 34.14 | 0
51 | CHIC 115001 | E7 General | Renew vent with PVC | 0 | No | 8.27 | 0
52 | CHIC 115005 | E7 General | Renew clay or concrete air vent | 0 | No | 11.31 | 0
53 | CHIC 130001 | E1 Roofs | Renew chimney pot | 0 | No | 183.91 | 0
54 | CHIC 13001 | E5 Environmental | Renew concrete step | 0 | IT | 116.47 | 0
55 | CHIC 13003 | E5 Environmental | Renew step in concrete paving | 0 | IT | 116.47 | 0
56 | CHIC 17403 | E5 Environmental | Renew chainlink fence and posts 1.8m high | 0 | M | 38.05 | 0
57 | CHIC 17407 | E5 Environmental | Renew chainlink fence on existing posts 1.8m high | 0 | M | 13.22 | 0
58 | CHIC 19003 | E5 Environmental | Refix loose fence post | 0 | No | 5.88 | 0
59 | CHIC 19005 | E5 Environmental | Renew timber fence post | 0 | No | 27.36 | 0
60 | CHIC 19013 | E5 Environmental | Renew PCC fence post over 1.5m | 0 | No | 40.49 | 0
61 | CHIC 213003 | E1 Roofs | Renew roof with corrugated reinforced cement sheets | 0 | M2 | 39.5 | 0
62 | CHIC 25001 | E5 Environmental | Renew timber gate post | 0 | No | 36.52 | 0
63 | CHIC 3007 | E5 Environmental | Renew 100mm concrete path | 36 | M2 | 65.83 | 2369.88 | 6: 3; 7: 3; 10: 10; 13: 2; 15: 5; 17: 2; 18: 1; 20: 10
64 | CHIC 3009 | E5 Environmental | Extra over for non slip finish to path | 0 | M2 | 8.1 | 0
65 | CHIC 303005 | E1 Roofs | Renew fascia/barge board n.e. 300mm wide | 0 | M | 14.03 | 0
66 | CHIC 328103 | E5 Environmental | Renew FL and B door | 0 | No | 290.67 | 0
67 | CHIC 33101 | E5 Environmental | Install 100mm clay drain ne 1m deep | 0 | M | 43.38 | 0
68 | CHIC 35003 | E5 Environmental | Install PVCu back inlet gully | 0 | No | 53.46 | 0
69 | CHIC 35007 | E5 Environmental | Renew gully surround any type | 0 | No | 162.97 | 0
70 | CHIC 35009 | E5 Environmental | Renew gully grate | 0 | No | 12.15 | 0
71 | CHIC 37015 | E5 Environmental | Rebed manhole cover and frame | 0 | No | 29.12 | 0
72 | CHIC 42021 | E2 External Walls | Apply render dub out in patch | 0 | IT | 25.83 | 0
73 | CHIC 421001 | E2 External Walls | Hack off render in patch | 0 | IT | 25.83 | 0
74 | CHIC 421003 | E2 External Walls | Hack off render | 0 | M2 | 20.26 | 0
75 | CHIC 421023 | E2 External Walls | Apply render dub out | 0 | M2 | 20.26 | 0
76 | CHIC 423001 | E2 External Walls | Repair crack in render | 0 | M | 7.6 | 0
77 | CHIC 423003 | E2 External Walls | Repair render to reveals | 0 | M | 10.63 | 0
78 | CHIC 423007 | E2 External Walls | Renew bellcast feature | 0 | M | 15.19 | 0
79 | CHIC 438201 | E6 Cylical Decoration | Oil paint external woodwork | 231 | M | 2.7 | 623.7 | 1: 18; 8: 51; 12: 42; 15: 20; 16: 24; 17: 8; 18: 23; 19: 23; 22: 22
80 | CHIC 438203 | E6 Cylical Decoration | Oil paint external woodwork | 38 | M2 | 6.38 | 242.44 | 6: 38
81 | CHIC 450101 | E6 Cylical Decoration | Masonary paint | 452 | M2 | 7.2 | 3254.4 | 1: 16; 8: 260; 11: 23; 12: 7; 13: 22; 14: 22; 15: 30; 16: 13; 17: 10; 22: 31; 23: 8; 24: 10
82 | CHIC 450257 | E6 Cylical Decoration | Stain external woodwork | 0 | M2 | 7.62 | 0
83 | CHIC 601105 | E1 Roofs | Renew downpipe | 0 | M | 5.07 | 0
84 | CHIC 601119 | E1 Roofs | Renew downpipe bracket | 0 | No | 4.56 | 0
85 | CHIC 603101 | E1 Roofs | Renew 112mm gutter | 0 | M | 6.13 | 0
86 | CHIC 7005 | E5 Environmental | Lift and rebed single PPC paving flag | 0 | No | 8.48 | 0
87 | CHIC 7007 | E5 Environmental | Lift and rebed PPC paving flags | 0 | M2 | 8.48 | 0
88 | CHIC 7011 | E5 Environmental | Renew PPC paving flags | 0 | SM | 28.9 | 0
89 | CHIC 7019 | E5 Environmental | Repoint PPC paving flags | 0 | M2 | 13.12 | 0
90 | CHIC A - H RENEW | E1 Roofs | Remove roof tiles, felt and battens, refit new tiles | 0 | M2 | 34.43 | 0
91 | CHIC A + G | E1 Roofs | Remove existing and fit new roof tiles | 0 | M2 | 37.46 | 0
92 | CHIC AB | E1 Roofs | Renew 150 lead flashing horizontal | 0 | M | 14.36 | 0
93 | CHIC AE | E1 Roofs | Rake out and repoint verge | 0 | M | 14.28 | 0
94 | CHIC AH | E1 Roofs | New loft insulation 150mm thick | 0 | M2 | 4.05 | 0
95 | CHIC A-H REFIX | E1 Roofs | Remove roof tiles, felt and battens, refit tiles | 0 | M2 | 24.46 | 0
96 | CHIC AL | E1 Roofs | Repoint chimney | 0 | M2 | 34.09 | 0
97 | CHIC AN | E1 Roofs | Rebed pots and flaunch chimney | 0 | No | 28.41 | 0
98 | CHIC AP | E9 Scaffold | Scaffold for roofing works | 0 | IT | 0 | 0
99 | CHIC G | E1 Roofs | Remove and rebed ridge tiles | 0 | M | 9.28 | 0
100 | CHIC H | E1 Roofs | Renew ridge and hip tiles | 0 | M | 12.05 | 0
101 | CHIC L | E1 Roofs | Supply and fix new valley tiles | 0 | M | 36.68 | 0
102 | CHIC Q | E1 Roofs | Running outlet | 0 | No | 1.01 | 0
103 | CHIC R | E1 Roofs | Stopped end | 0 | No | 1.01 | 0
104 | CHIC Rear | E4 Windows & Doors | New composite rear door and frame | 0 | No | 383 | 0
105 | CHIC S | E1 Roofs | Swan neck | 0 | No | 1.01 | 0
106 | CHIC T | E1 Roofs | Internal angle | 0 | No | 1.01 | 0
107 | CHIC V | E1 Roofs | Connection to existing rainwater drainage | 0 | No | 2.73 | 0
108 | CHIC W-Y | E1 Roofs | Renew soffit board n.e. 200mm wide | 0 | M | 16.78 | 0
109 | CJ001 | E2 External Walls | PLATE:RENEW 75X100MM WALL PLATE | 0 | LM | 6.12 | 0
110 | CJ003 | E1 Roofs | RAFTER:RENEW NE 175MM RAFTER OR JOIST | 0 | LM | 6.88 | 0
111 | CJ007 | E1 Roofs | FASCIA:RENEW IN SOFTWOOD NE 300MM | 0 | LM | 20.56 | 0
112 | CJ012 | E1 Roofs | FASCIA/SOFFIT/BARGE:REFIX | 0 | LM | 14.04 | 0
113 | CJ016 | E1 Roofs | FASCIA: OVERCAP IN PVCU NE 300MM - HOUSE/BUNGALOW (2 ELEVATIONS) COMPLETE | 0 | IT | 157.15 | 0
114 | CJ018 | E1 Roofs | FASCIA/BARGE: RENEW IN PVCU NE 300MM - OUTBUILDING/DETACHED SHED/CANOPY | 0 | LM | 15.71 | 0
115 | CJ024 | E4 Windows & Doors | BOXED END:RENEW IN PVCU TO FASCIA AND SOFFIT | 0 | NO | 25.05 | 0
116 | CJ027 | E1 Roofs | CLADDING:RENEW 19MM SHIPLAP NE 2.0SM | 6 | IT | 51.89 | 311.34 | 2: 1; 3: 1; 4: 1; 5: 1; 6: 2
117 | CJ034 | E1 Roofs | CLADDING:RENEW TGV JOINT OVER 2.0SM | 0 | SM | 29.64 | 0
118 | CJ041 | E4 Windows & Doors | FRAME:RENEW PVCU COMBINATION UNIT | 0 | SM | 208.92 | 0
119 | CJ054 | E4 Windows & Doors | WINDOW:RENEW GLAZING BEAD | 0 | LM | 4.27 | 0
120 | CJ100 | E4 Windows & Doors | WINDOW:CLEAN PVCU WINDOW ANY TYPE EXT SIDE | 0 | IT | 3.16 | 0
121 | CJ115 | E4 Windows & Doors | DOOR:RENEW L AND B DOOR | 0 | NO | 143.62 | 0
122 | CJ135 | E4 Windows & Doors | DOOR:OVERHAUL EXTERNAL COMPLETE | 0 | NO | 46.95 | 0
123 | CJ157 | E4 Windows & Doors | FRAME:RENEW EXTERNAL DOOR COMPLETE | 0 | NO | 96.73 | 0
124 | CJ174 | E4 Windows & Doors | FRAME:REFIX LOOSE EXTERNAL FRAME | 0 | NO | 19.56 | 0
125 | DR010 | E1 Roofs | GULLY:INSTALL PVCU BACK INLET GULLY | 0 | NO | 63.31 | 0
126 | DR012 | E1 Roofs | GULLY:RENEW ANY TYPE SURROUND AND KERB | 0 | NO | 14.06 | 0
127 | DR029 | E5 Environmental | MANHOLE:RENEW COVER MEDIUM GRADE 610X457MM | 0 | NO | 63.72 | 0
128 | EWS 1 |  | Gas Flue - turn off appliances then check, certify and turn back on | 0 | 0 | 239.27 | 0
129 | EWS 10 |  | meter box clean | 0 | 0 | 2.03 | 0
130 | EWS 11 |  | renew Aerial Bracket | 0 | 0 | 50.64 | 0
131 | EWS 12 |  | SHED Old Stain - New Stain | 0 | 0 | 46.02 | 0
132 | EWS 13 |  | Painting - Gate | 0 | 0 | 17.59 | 0
133 | EWS 14 |  | Guttering - square to round connection | 0 | 0 | 7.41 | 0
134 | EWS 15 |  | Renew Valley, make good tiles | 0 | IT | 423.8 | 0
135 | EWS 16 |  | Install Soak away | 0 | 0 | 242.5 | 0
136 | EWS 17 |  | Install RW pipe | 0 | 0 | 139.77 | 0
137 | EWS 18 |  | Sweep Path Whole Property | 0 | IT | 12.66 | 0
138 | EWS 19 |  | arial istaller revisit | 0 | 0 | 40.51 | 0
139 | EWS 2 |  | Gas Flue - one off inspection | 0 | 0 | 106.97 | 0
140 | EWS 20 |  | replace rotton timber battens | 0 | 0 | 174.64 | 0
141 | EWS 21 |  | Clean gully | 0 | 0 | 14 | 0
142 | EWS 22 |  | Day Rate | 0 | 0 | 20.26 | 0
143 | EWS 23 |  | refix cable | 0 | 0 | 27.85 | 0
144 | EWS 24 |  | Remove stump | 0 | 0 | 178.94 | 0
145 | EWS 25 |  | Refix door frame | 0 | 0 | 40.11 | 0
146 | EWS 26 |  | PVC trim to window | 0 | 0 | 6.53 | 0
147 | EWS 27 |  | Renew Hopper head | 0 | 0 | 30.06 | 0
148 | EWS 28 |  | MAKE SAFE ELECTRICS | 0 | 0 | 83.56 | 0
149 | EWS 3 |  | Gas Flue - Turn off - check, certify and turn back on | 0 | 0 | 132.29 | 0
150 | EWS 4 |  | Compound set up for remote working area | 0 | 0 | 70.9 | 0
151 | EWS 5 |  | Renew Soffit - exceeding 200mm but less than 400mm wide | 0 | 0 | 16.78 | 0
152 | EWS 6 |  | Apply bitumen paint to brickwork | 0 | 0 | 4.71 | 0
153 | EWS 7 |  | Install Pea Gravel Channel | 0 | 0 | 33.91 | 0
154 | EWS 8 |  | waste removal | 0 | 0 | 101.28 | 0
155 | EWS 9 |  | Ridge Renew Vent | 0 | IT | 130.35 | 0
156 | FE004 |  | FENCING:RENEW 1.8M BOARD PCC POST | 0 | LM | 65.59 | 0
157 | FE005 |  | FENCING:RENEW 1.8M BOARD PCC POST GRAVEL BOARD | 0 | LM | 67.62 | 0
158 | FE006 |  | FENCING:RENEW 1.8M BOARD-TIMBER POST | 0 | LM | 60.39 | 0
159 | FE007 |  | FENCING:RENEW SOFTWOOD RAIL | 0 | NO | 12.71 | 0
160 | FE011 |  | FENCING:RENEW VERTICAL BOARD-1.675M | 0 | NO | 3.97 | 0
161 | FE014 |  | FENCING:RENEW TIMBER GRAVEL BOARD | 0 | NO | 8.03 | 0
162 | FE024 |  | FENCING:RENEW 1.8M HIGH PANEL | 0 | NO | 41 | 0
163 | FE025 |  | FENCING:RENEW 1.2M HIGH PANEL | 0 | NO | 35.28 | 0
164 | FE029 |  | FENCING:ERECT 1.2M HIGH PANEL WITH TIMBER POSTS | 0 | LM | 36.9 | 0
165 | FE034 |  | FENCING:REMOVE PANEL FENCE COMPLETE | 0 | LM | 4.26 | 0
166 | FE036 |  | CHAINLINK:ERECT FENCE AND POSTS 1.8M | 0 | LM | 32.82 | 0
167 | FE039 |  | CHAINLINK:REMOVE COMPLETE | 0 | LM | 4.26 | 0
168 | FE053 |  | FENCING:RENEW WIRES TO EXISTING POSTS 1.2M | 0 | LM | 3.4 | 0
169 | FE056 |  | FENCING:MAKE SAFE FENCING | 0 | LM | 7.83 | 0
170 | FE061 |  | FENCE POST:REFIX LOOSE POST | 0 | NO | 5.57 | 0
171 | FE069 |  | GATE:RENEW TIMBER NE 1.0SM | 0 | NO | 101.5 | 0
172 | FE071 |  | GATE:RENEW PAIR TIMBER NE 2.5SM OVERALL | 0 | NO | 203.74 | 0
173 | FE073 |  | GATE:INSTALL TIMBER NE 1.5SM | 0 | NO | 189.51 | 0
174 | FE075 |  | GATE:REPAIR AND EASE AND ADJUST TIMBER GATE | 2 | NO | 13.87 | 27.74 | 5: 2
175 | FE079 |  | GATE:RENEW METAL NE 1.0SM | 0 | NO | 75.95 | 0
176 | FE081 |  | GATE:REPAIR AND EASE AND ADJUST METAL GATE | 0 | NO | 10.07 | 0
177 | FE087 |  | GATE POST AND GATE:RENEW AND REPAIR ANY FITTING | 0 | NO | 8.81 | 0
178 | GL035 |  | DOUBLE GLAZED UNIT:REGLAZE NE 1.00SM-SAFETY LOW E | 0 | NO | 97.64 | 0
179 | GR002 |  | PATH:RENEW 100MM CONCRETE BED | 0 | SM | 50.82 | 0
180 | GR004 |  | PATH:REMOVE AND INFILL WITH TOPSOIL | 0 | SM | 29.89 | 0
181 | GR008 |  | FLAG:EXCAVATE AND LAY NEW PRECAST CONCRETE | 0 | SM | 34.7 | 0
182 | GR010 |  | FLAGS:LIFT AND REBED PCC PAVING | 0 | SM | 14.18 | 0
183 | GR011 |  | FLAG:RENEW SINGLE PCC PAVING | 0 | NO | 8.22 | 0
184 | GR012 |  | FLAGS:RENEW PCC PAVING | 0 | SM | 23.87 | 0
185 | GR017 |  | PAVING:REBED BRICK PAVING-SAND | 0 | SM | 35.56 | 0
186 | GR024 |  | HARDCORE:ADDITIONAL SUB-BASE OR BED NE 150 | 0 | SM | 17.42 | 0
187 | GR030 |  | STEP:REPAIR DAMAGED CONCRETE | 0 | IT | 10.61 | 0
188 | GR035 |  | BALUSTRADE:SUPPLY AND FIX KEE KLAMP | 0 | LM | 55.76 | 0
189 | ma003 |  | SURFACES:REPAIR CRACKS CONCRETE NE 10MM | 0 | SM | 165.45 | 0
190 | MA005 |  | SURFACES:REPAIR CRACKS CONCRETE NE 15MM | 0 | SM | 240.66 | 0
191 | NHF-6 10 |  | lay new turf 460401 | 0 | 0 | 8.66 | 0
192 | NHF-6 11 |  | Silicone Sealant | 0 | 0 | 3.71 | 0
193 | NHF-6 12 |  | Repair SV Pipe 610129 | 0 | 0 | 118.27 | 0
194 | NHF-6 13 |  | Install Aco Drain | 0 | 0 | 30.62 | 0
195 | NHF-6 14 |  | Clean out Gutter 603903 | 0 | 0 | 27.72 | 0
196 | NHF-6 15 |  | Refix RWP 601121 | 0 | 0 | 18.83 | 0
197 | NHF-6 16 |  | Temp repair header Tank 665011 | 0 | 0 | 21.36 | 0
198 | NHF-6 17 |  | Remove Bush | 0 | 0 | 46.7 | 0
199 | NHF-6 18 |  | Ladder frame / Studwork for new Soffit 301301 | 0 | 0 | 174.64 | 0
200 | NHF-6 19 |  | Skip & clear Garden 460101 | 0 | 0 | 409.92 | 0
201 | NHF-6 2 |  | Elevations 603903 | 0 | 0 | 27.72 | 0
202 | NHF-6 20 |  | Relay loft insulation 227007 | 0 | 0 | 8.19 | 0
203 | NHF-6 21 |  | Install water butt to rear | 0 | 0 | 242.5 | 0
204 | NHF-6 3 |  | Renew Ballon to sv pipe | 0 | 0 | 22.25 | 0
205 | NHF-6 4 |  | Install Kee klamp fence to step | 0 | 0 | 81.68 | 0
206 | NHF-6 5 |  | Paint Stairwell 493-90 | 0 | 0 | 585.26 | 0
207 | NHF-6 6 |  | re-attach 2 rivers sign to fence 29301 | 0 | 0 | 16.41 | 0
208 | NHF-6 7 |  | 943019 | 0 | 0 | 81.68 | 0
209 | NHF-6 8 |  | Core Drill hole in wall | 0 | IT | 64.08 | 0
210 | NHF-6 9 |  | Renew Gas Flue 709013 | 0 | 0 | 34.28 | 0
211 | PA001 |  | SEALER:APPLY ONE COAT TO WALLS AND CEILINGS | 0 | SM | 2.71 | 0
212 | PA004 |  | WALLS:BRUSH AND WASH DOWN | 16 | SM | 5.23 | 83.68 | 1: 16
213 | PA007 |  | WINDOWS: WASHDOWN AND CLEAN PVCU | 0 | SM | 1.74 | 0
214 | PA008 |  | DOORS: WASHDOWN AND CLEAN PVCU | 0 | IT | 3.47 | 0
215 | PA010 |  | FASCIAS AND BARGEBOARDS: WASHDOWN AND CLEAN PVCU | 48 | LM | 0.69 | 33.12 | 7: 3; 18: 2; 19: 2; 21: 41
216 | PA014 |  | GATES:PREPARE PAINT GATE AND POSTS | 0 | IT | 13.62 | 0
217 | PA015 |  | BALUSTRADING:PREPARE PAINT SURFACES | 114 | SM | 12.68 | 1445.52 | 12: 60; 15: 10; 18: 7; 19: 5; 23: 32
218 | PA018 |  | PIPEWORK:PREPARE PAINT NE300MM | 0 | LM | 1.38 | 0
219 | PA021 |  | DOOR:PREPARE PAINT TIMBER DOOR (OS) | 0 | IT | 24.21 | 0
220 | PA024 |  | DOOR:PREPARE 3 COATS STAIN TO DOOR (OS) | 0 | IT | 15.81 | 0
221 | PA025 |  | DOOR:PREPARE 3 COATS STAIN TO DOOR (BS) | 128 | IT | 28.01 | 3585.28 | [5 empty] | 24 |  | 8 | 8 |  | 8 | 10 | 8 | 2 | 2 | 4 | 4 | 8 | 8 | 4 | 6 | 8 | 8 | 8
221a | PA025a |  | Frame: prepare and paint door frame | 128 | IT | 19.14 | 2449.92 | [5 empty] | 24 |  | 8 | 8 |  | 8 | 10 | 8 | 2 | 2 | 4 | 4 | 8 | 8 | 4 | 6 | 8 | 8 | 8
222 | PA028 |  | FENCING:PREPARE 3 COATS STAIN NE 300MM | 582 | LM | 4.52 | 2630.64 | 2: 68; 3: 79; 4: 114; 5: 55; 6: 70; 7: 117; 10: 20; 13: 8; 16: 16; 17: 32; 21: 3
223 | PA029 |  | GATES:PREPARE 2 COATS STAIN TO GATES POSTS | 0 | IT | 9.07 | 0
224 | PA030 |  | CILLS: APPLY TILE PAINT | 0 | LM | 1.75 | 0
225 | PA031 |  | STEPS: APPLY TILE PAINT | 0 | LM | 3.28 | 0
226 | PL003 |  | WALL:APPLY RENDER DUB OUT IN PATCH | 0 | IT | 18.32 | 0
227 | PL010 |  | WALL:APPLY DECORATIVE RENDER DUB | 0 | SM | 22.35 | 0
228 | PL014 |  | RENDER REPAIRS:RENEW BELLCAST FEATURE | 0 | LM | 7.71 | 0
229 | PLU003 |  | GUTTER AND DOWNPIPE COMPLETE:RENEW NE 112MM PVCU COMPLETE NE 2 STOREY | 0 | LM | 18.67 | 0
230 | PLU005 |  | GUTTER:REALIGN PVCU GUTTER | 200 | LM | 4.66 | 932 | 1: 18; 8: 51; 12: 42; 13: 1; 15: 20; 16: 16; 17: 8; 22: 44
231 | plu006 |  | STACK:RENEW EXTERNAL PVCU COMPLETE NE 2 STOREY | 0 | IT | 187.37 | 0
232 | PLU017 |  | WASTE:RENEW 40MM PIPE | 0 | LM | 9.4 | 0
233 | RO004 |  | ROOF TILE:REMOVE AND REFIX INTERLOCKING NE 5 NO | 0 | IT | 4.55 | 0
234 | RO006 |  | ROOF TILE:REFIX INTERLOCKING RENEW FELT BATTENS | 0 | SM | 17.52 | 0
235 | RO007 |  | ROOF TILE:OVERHAUL INTERLOCKING ROOF COMPLETE | 0 | SM | 13.36 | 0
236 | RO008 |  | ROOF TILE:RENEW PLAIN CONCRETE OR CLAY NE 10 NO | 0 | IT | 9.98 | 0
237 | RO010 |  | ROOF TILE:RENEW PLAIN FELT AND BATTENS | 0 | SM | 72.94 | 0
238 | RO012 |  | ROOF TILE:REMOVE AND REFIX PLAIN OVER 10 NO | 0 | SM | 24.9 | 0
239 | RO013 |  | ROOF TILE:REFIX PLAIN RENEW FELT, BATTENS | 0 | SM | 42.31 | 0
240 | RO014 |  | ROOF TILE:OVERHAUL PLAIN TILE ROOF COMPLETE | 0 | SM | 13.36 | 0
241 | RO015 |  | VERGE:RAKE OUT AND REPOINT IN MORTAR | 0 | LM | 10.96 | 0
242 | RO018 |  | VERGE:RENEW PLAIN TILE VERGE | 0 | LM | 18.2 | 0
243 | RO020 |  | RIDGE:RENEW HALF ROUND BEDDED TILE | 0 | LM | 31.74 | 0
244 | RO031 |  | VERGE:RENEW DRY VERGE COMPLETE | 0 | LM | 22.35 | 0
245 | RO034 |  | VERGE:RENEW OR REFIX DRY VERGE RIDGE END | 0 | NO | 7.99 | 0
246 | RO037 |  | RIDGE:RENEW DRY RIDGE TILES | 0 | LM | 30.41 | 0
247 | RO038 |  | RIDGE:RENEW DRY RIDGE GAS FLUE TERMINAL | 0 | NO | 92.02 | 0
248 | RO039 |  | VENT:RENEW VENT ROOF TILE UNIT | 0 | NO | 33.25 | 0
249 | RO043 |  | VENT:RENEW EAVES VENTILATORS | 0 | LM | 16.68 | 0
250 | RO044 |  | SLATE:RENEW FIBRE CEMENT NE 5 NO | 0 | IT | 13.09 | 0
251 | RO045 |  | SLATE:RENEW FIBRE CEMENT OVER 5 NO | 0 | SM | 31.14 | 0
252 | RO059 |  | RIDGE:RENEW MONO-PITCH TO SLATING | 0 | LM | 97.29 | 0
253 | RO085 |  | ROOF: DEMOSS ROOF COVERING | 0 | SM | 8.88 | 0
254 | RO088 |  | ROOF:SWEEP AND APPLY BITUMEN | 0 | SM | 7.66 | 0
255 | RO099 |  | ROOF:FIX ROOF LEAK TO PITCHED ROOF | 0 | IT | 48.44 | 0
256 | RO118 |  | FELT:RENEW CHIPPINGS | 0 | SM | 9.69 | 0
257 | RO120 |  | FELT:RENEW HP STONE CHIPPINGS 3L | 0 | SM | 33.57 | 0
258 | RO151 |  | SLATE:RENEW LEAD TO PIPE | 0 | NO | 31.02 | 0
259 | RO152 |  | SLATE:RENEW PROPRIETARY TO PIPE | 0 | NO | 38.31 | 0
260 | RO153 |  | FLASHING:RENEW LEAD COVER NE 150MM | 0 | LM | 14.61 | 0
261 | RO155 |  | FLASHING:RENEW LEAD STEPPED NE 225MM | 0 | LM | 26.8 | 0
262 | RO156 |  | FLASHING:RENEW LEAD APRON NE 300MM | 0 | LM | 25.52 | 0
263 | RO157 |  | FLASHING:TAKE OFF AND REFIX LEAD | 0 | LM | 7.75 | 0
264 | SC012 |  | SCAFFOLD TOWER:PROVIDE NE 10M HIGH | 13 | IT | 130.29 | 1693.77 | 1: 4; 2: 1; 3: 1; 4: 1; 5: 1; 6: 1; 7: 1; 16: 1; 23: 1; 24: 1
265 | SC015 |  | SCAFFOLD TOWER:MOVE POSITION | 2 | IT | 55.36 | 110.72 | 1: 2
266 | SC017 |  | SCAFFOLDING:PROVIDE TO CHIMNEY NE 10M HIGH | 0 | IT | 110.93 | 0
267 | SC027 |  | RUBBISH CHUTE:PROVIDE 10M HIGH | 0 | IT | 38.21 | 0
268 | SP024 |  | TEMPORARY REPOSITIONING AND REINSTATEMENT OF TEANANTS SATELLITE DISHES TO FACILITATE WORKS | 0 | IT | 81.68 | 0
269 | v11 |  | Hip:Renew - dry system | 0 | LM | 27.91 | 0
270 | v12 |  | Reinstate party wall | 0 | IT | 75.96 | 0
271 | v13 |  | Make good around purlin on party wall | 0 | IT | 50.64 | 0
272 | v14 |  | Make good to canopy | 0 | IT | 101.28 | 0
273 | v15 |  | CUT BACK FOLIAGE TO REAR | 0 | IT | 30.38 | 0
274 | v17 |  | CLEAN SVP | 0 | LM | 4.05 | 0
275 | v18 |  | CLEAN CONSERVATORY | 0 | IT | 30.38 | 0
276 | v19 |  | RENEW LEAD SLATE TO SVP | 0 | No | 33.25 | 0
277 | v20 |  | CLEAN UPVC TO OUTHOUSE | 0 | LM | 0.69 | 0
278 | V21 |  | Electrical Isolation | 0 | IT | 75.96 | 0
279 | v22 |  | Redland rapid lead flashing | 0 | SM | 43.95 | 0
280 | v23 |  | SWEEP CHIMNEY | 0 | IT | 109.38 | 0
281 | v24 |  | HOPPER | 0 | No | 33.07 | 0
282 | v26 |  | INSTALL ACCO DRAIN | 0 | LM | 81.68 | 0
283 | v27 |  | Path - sweep & clean debris away | 0 | LM | 13.93 | 0
284 | v28 |  | Solid fuel initial inspection | 0 | No | 86.09 | 0
285 | V3 |  | E/O Boarded lift semi | 0 | IT | 207.62 | 0
286 | v30 |  | REDRESS LEADWORK TO CHIMNEY | 0 | LM | 25.52 | 0
287 | v31 |  | REALIGN GUTTER BRACKETS | 0 | LM | 4.66 | 0
288 | v32 |  | Gas - Complete Initial Check of Property | 0 | IT | 213.94 | 0
289 | v33 |  | Gas - Recommission Boiler/Fire following roof works | 0 | IT | 264.58 | 0
290 | v34 |  | Brickwork - Paint - Bitumen - Below DPC | 0 | LM | 4.71 | 0
291 | v35 |  | Clean Meter Box | 0 | IT | 2.03 | 0
292 | v36 |  | Outside Security Light | 0 | IT | 75.96 | 0
293 | V4 |  | Chimney Scaffold single storey | 0 | IT | 278.52 | 0
294 | V5 |  | Chimney Scaffold 2 storey | 0 | IT | 349.42 | 0
295 | S2 |  | Complete Initial Check of Property | 0 | 0 | 106.97 | 0
296 | S3 |  | Demolish Outhouse | 0 | 0 | 0.01 | 0
297 | S4 |  | FENCING AND HANDRAIL TO BE FITTED | 0 | 0 | 0.01 | 0
298 | S5 |  | GUTTER SQUARE TO ROUND | 0 | 0 | 7.41 | 0
299 | S6 |  | Hip:Renew - dry hip system | 0 | 0 | 3.54 | 0
300 | S7 |  | Hip:Renew - dry ridge system | 0 | 0 | 12.15 | 0
301 | S8 |  | RE CLIP CABLE | 0 | 0 | 27.85 | 0
302 | S9 |  | Recommission Boiler/Fire following roof works | 0 | 0 | 132.29 | 0
303 | S10 |  | RETAINING WALL HAS STARTED TO SHIFT | 0 | 0 | 0.01 | 0
304 | S11 |  | Ridge:Renew vent | 0 | 0 | 130.35 | 0
305 | S12 |  | Ridge-roof vent | 0 | 0 | 130.35 | 0
306 |  |  | ADDED IN ITEMS OVER AND ABOVE MOST USED
307 | SHED1 |  | Re-locate shed due to work, re-position following works | 0 | IT | 126.6 | 0
308 | PA019 |  | SURFACES:PAINT GENERAL SURFACES TIMBER | 0 | SM | 11.38 | 0
309 | FE040 |  | CHAINLINK:RESECURE LOOSE FENCE | 0 | LM | 0.79 | 0
310 | NHF 871507 |  | 0 | 0 | 0 | 0 | 0
311 | RO103 |  | FELT:RENEW HP PLAIN OR MINERAL FINISH 2L | 0 | SM | 18.41 | 0
312 | RO163 |  | VALLEY:RENEW LEAD GUTTER AND BOARDS | 0 | LM | 65.04 | 0
313 | PA023 |  | SURFACES:PREPARE 3 COATS DECORATIVE WOOD STAIN | 130 | SM | 9.71 | 1262.3 | 2: 20; 3: 20; 4: 20; 5: 20; 6: 50
314 | DR043 |  | SOAKAWAY:CLEAR EXISTING | 0 | CM | 118.1 | 0
315 | CJ116 |  | DOOR:RENEW FL AND B DOOR | 0 | NO | 159.43 | 0
316 | MA025 |  | LINTELS/CILLS:REPAIR CRACKS STONEWORK NE 15MM | 0 | LM | 46.35 | 0
317 | v29 |  | RUBBISH CHUTE | 0 | IT | 38.21 | 0
318 | RO067 |  | TILE:REFIX HANGING - RENEW FELT AND BATTENS | 0 | SM | 29.08 | 0
319 | CJ028 |  | CLADDING:RENEW 19MM SHIPLAP OVER 2.0SM | 0 | SM | 29.8 | 0
320 | BR085 |  | Duchess with georgian décor legs | 0 | IT | 213.7 | 0
321 | BR112 |  | CHIMNEY:RENEW TWO COAT RENDER TO STACK | 0 | SM | 25.53 | 0
322 | BR122 |  | CHIMNEY:RENEW GALVANISED WIRE BIRDCAGE | 0 | NO | 19.71 | 0
323 | CAN1 |  | Paint canopy | 0 | IT | 41.95 | 0
324 | DBAT |  | Double battens to roof | 0 | m2 | 12.15 | 0
325 | TT |  | Temporary tar up gable end due to birds | 0 | IT | 81.02 | 0
326 | V39 |  | Supply and fit 100mm insulation to gable end | 0 | m2 | 114.85 | 0
327 | V40 |  | 0 | 0 | 0 | 0 | 0
328 | V41 |  | Lead Slate for Gas Flue | 0 | No | 99.36 | 0
329 | V42 |  | MG Chainlink Fence Front and Side | 0 | LM | 3.18 | 0
330 | V43 |  | Solid fuel recomission | 0 | IT | 86.09 | 0
331 | V44 |  | Replace Chimney Slab | 0 | IT | 129.03 | 0
332 | V45 |  | Refit Chimney pots | 0 | No | 11.06 | 0
333 | RO078 |  | SHEETING:RENEW CORRUGATED REINFORCED CEMENT | 0 | SM | 17.25 | 0
334 | V46 |  | Loft clearence. PC cost | 0 | IT | 101.28 | 0
335 | RO144 |  | INSULATION:LAY NEW 200MM THICK QUILT | 0 | SM | 7.62 | 0
336 | v47 |  | Demolish lean to shed. 12m2 roof covering. P.sum | 0 | IT | 253.2 | 0
337 | v48 |  | Remove concrete bunker. P.sum | 0 | SM | 11.76 | 0
338 | RO079 |  | SHEETING:RENEW CLEAR PLASTIC | 0 | SM | 11.76 | 0
339 | CJ125 |  | EXTERNAL STORE/SHED/OUTBUILDING DOOR AND FRAME | 0 | NO | 200.71 | 0
340 | CJ097 |  | WINDOW:RENEW CILL TO PVCU | 0 | LM | 10.85 | 0
341 | FE059 |  | FENCING:FIX GALVANISED REPAIR BRACKET | 0 | NO | 4.06 | 0
342 | RO167 |  | ROOF:RENEW LEAD ROOF COVERING | 0 | SM | 57.66 | 0
343 | SN1 |  | Flaunch Chimney | 0 | No | 127.4 | 0
344 | SN2 |  | Redress leadwork to chimney | 0 | LM | 28.12 | 0
345 | SN3 |  | Clean Canopy | 0 | No | 6.42 | 0
346 | SN4 |  | cut grass front and gardens | 0 | SM | 0 | 0
347 | SN5 |  | Cut hegdes to front, back and side gardens | 0 | m2 | 0 | 0
348 | SN6 |  | Clad Gable end isolated gable end with 100mm Kingspan | 0 | it | 0 | 0
349 | SN7 |  | Remove and refit large Canopy | 0 | IT | 0 | 0
350 | SN8 |  | Clad Cable end | 0 | IT | 0 | 0
351 | SN9 |  | Install new flue bracket - materials only | 0 | 0 | 0 | 0
352 | Snape10 | NHF-6 301301 | Renew Timber Rafer to take new soffit | 0 | lm | 86.22 | 0
353 | RO028 |  | Renew Roof Hip Iron | 0 | lm | 8.57 | 0
354 | Snape 11 |  | Renew Retaining bolts and cleats straining bar - chainlink fence | 0 | it | 20 | 0
355 | PLU014 |  | Renew Sink waste pipe 40mm | 0 | it | 33.33 | 0
356 | PA001 |  | SBR Bonding agent to walls | 0 | m2 | 2.67 | 0
357 | Snape 14 | NHF-6 001303 | Pea Gravel and Trench | 0 | LM | 21.27 | 0
358 | Snape 15 |  | Canopy as per Invoice - £795.00 + 15% | 0 |  | 914.25 | 0
359 | CJ116 |  | Supply and fit new shed door & ironmongery | 0 | No | 157.41 | 0
360 | CJ158 |  | Supply and fit new shed door frame | 0 | No | 118.46 | 0
361 | GR035 |  | Supply and fit handrails to steps - Kee Klamp | 0 | LM | 55.05 | 0
362 | CJ028 |  | Renew cladding to bay window | 0 | sm | 29.42 | 0
363 | Snape 20 |  | Wash down driveway | 0 | IT | 65 | 0
364 | Snape 21 |  | Supply Temp access steps - as per Invoice | 0 |  | 109.25 | 0
365 | Snape 22 | NHF-6 001501 | Lay new concrete edge to side of path | 0 | LM | 30.64 | 0
366 | DR034 |  | Gully unblock | 0 | No | 5.99 | 0
367 | Snape 24 |  | remove roof tiles, felt and battens, refit new slate tiles | 0 | m2 | 42 | 0
368 | CJ159 |  | FRAME:RENEW EXTERNAL DOOR FANLIGHT COMPLETE | 0 | No | 162.67 | 0
369 | CJ108 |  | DOOR:RENEW SW PANELLED OR GLAZED BACK DOOR | 0 | No | 271.39 | 0
370 | S27 |  | Renew render beads | 0 | LM | 12 | 0
371 | RO096 |  | Temporary Roof Covering - Slate Roof IT = 12m2 | 0 | IT | 32 | 0
372 | CJ137 |  | Temp Door | 0 | IT | 84.44 | 0
373 | Snape 28 |  | Supply new door | 0 | IT | 362.25 | 0
374 | BR102 |  | CHIMNEY:REBUILD 1 COURSE 4 FLUE | 0 | IT | 32.12 | 0
375 | RO011 |  | ROOF TILE:REMOVE AND REFIX PLAIN NE 10 NO | 0 | IT | 5.93 | 0
376 | Snape 29 |  | (Disregarded item/rate) | 0 | IT | 0 | 0
377 | RO100 |  | Fix Roof leak to flat roof | 0 | IT | 51.54 | 0
378 | Snape 30 |  | Clad plastick T&G Grove borads to window cheeks | 0 | m2 | 39.85 | 0
379 | Snape 31 |  | Deepflow guttering | 0 | lm | 28.05 | 0
380 | Snape 32 | PLU014 | WASTE:RENEW 40MM PIPE AND TRAP BASIN | 0 | NO | 31.19 | 0
381 | Snape 33 |  | clean foam from rafters and put into skip | 0 | m2 | 18.5 | 0
382 | CJ210 |  | DOOR FURNITURE:SUPPLY NEW SET OF LEVER HANDLES | 0 | NO | 11.37 | 0
383 | GR005 |  | MACADAM:EXCAVATE AND LAY 70MM PAVING | 0 | m2 | 28.61 | 0
384 | Snape 34 |  | Flue Bracket - Element for materials only | 0 | NO | 20 | 0
385 | Snape 35 |  | Replaster Kitchen ceiling | 0 | M2 | 38.52 | 0
386 | Snape 36 | ABS Code | Wire mesh to support brickwork | 0 | m2 | 29.2 | 0
387 | Chic 421021 |  | Dub out and patch render | 0 | IT | 27.9 | 0
388 | Scaffold Adjusted |  | Scaffold for roofing works (holding point cost) | 0 | IT | 939.64 | 0
389 | CHIC 323603 |  | Fit new PVC door | 0 | IT | 666.59 | 0
390 | Snape 37 | ABS Code | Renew Copper Value | 0 | IT | 57.06 | 0
391 | FE037 |  | Chainlink: Renew on exisiting posts 1.2M | 0 | LM | 9.41 | 0
392 | Snape 38 | NHF-6 301107 | Renew Joist in roof Space | 0 | NO | 28 | 0
393 | CJ053 |  | Window Cill: Prep Window | 0 | IT | 25.5 | 0
394 | BR033 |  | Pier: Rebuild 1-1/2B isolated in facings | 0 | IT | 91.97 | 0
395 | Snape 39 | NHF-6 219001 | Renew Roof Structure using EPDM | 0 | IT | 239.57 | 0
396 | Snape 40 | Quote 36 | New Ridges | 0 | LM | 48.2 | 0
397 | Snape 41 | Quote 36 | Existing Ridges | 0 | LM | 19.8 | 0
398 | Snape 42 | Quote 34 | Renew Ridges with new dry fix system | 0 | lm | 75.56 | 0
399 | Snape 43 | ABS Code | Shift 600 tiles around 3no roofs to allow the reclaim tiles to be used not new tiles - 2 men 1 day | 0 | No | 404.8 | 0
400 | Snape 44 | ABS Code | 2 men needed to lift 900 x 600 slabs for legal manual handling reasons - 2 men x 1 day | 0 | NO | 404.8 | 0
401 | Snape 45 | ABS Code | Provide road mats to protect ground to site - 18no mats cost £340 for 1 week. Transport £50 each way = £100 | 0 | NO | 440 | 0
402 | CD1 | Comm. Dec's | Gloss Paint | 112 | LM | 8.54 | 956.48 | 6: 3; 11: 43; 22: 66
403 | CD2 | Comm. Dec's | Emulsion Paint | 802 | M2 | 6.33 | 5076.66 | 6: 186; 11: 222; 18: 29; 19: 29; 21: 5; 22: 291; 23: 20; 24: 20
404 | BR095 |  | Supply and install pipeducts for drainage | 0 | IT | 42.28 | 0
405 | Snape 49 |  | Bonding Valley | 0 | IT | 223.86 | 0
406 | Snape 50 | Quote 42 | Cap off flue and fill with Vermiculate - 3 bags @ £25 + 2hrs labour | 0 | NO | 135.65 | 0
407 | Snape 51 | Quote 43 | Ridge/Verge joint end cap on Dry Ridge & Verge system | 0 | NO | 24.3 | 0
408 | CJ036 |  | Cladding: Renew PVC Shiplap Over 2.0sm | 0 | m2 | 31.93 | 0
409 | CJ051 |  | WINDOW FRAME:CUT OUT AND SPLICE NEW SECTION | 0 | LM | 29.96 | 0
410 | CJ173 |  | FRAME:SPLICE EXTERNAL REPAIR NE 1.0M | 0 | No | 25.82 | 0
411 | Snape 52 |  | Demolish Existing flat roof | 0 | No | 347.76 | 0
412 | Scaffold Adjusted |  | Scaffold for roofing works (holding point cost) 1 Lift | 0 | IT | 1000 | 0
413 | Scaffold Adjusted |  | Scaffold for roofing works (holding point cost) 2 Lift | 3 | IT | 1500 | 4500 | bar: 8; 12; 22